## Sheet1
Task Name | Predecessors | Duration | Start | Finish | Resource Names | Work
Personal Health Monitoring System |  | 66 days | Thu 09-10-20 | Thu 12-10-20 | C[1],D[1],H[1],S[1],W[1] | 2,155 hrs
Requirement Analysis |  | 8 days | Thu 09-10-20 | Mon 09-21-20 |  | 179 hrs
Meeting with developers/testers and On-boarding process |  | 1 day | Thu 09-10-20 | Thu 09-10-20 | AK,MR,CM,AL,TS,HS | 3 hrs
Technical Requirements | 3 | 2 days | Fri 09-11-20 | Mon 09-14-20 | AK,AL,HS,CM,MR,TS | 96 hrs
Design Requirements | 4 | 1 day | Tue 09-15-20 | Tue 09-15-20 | AK,AL,W[1] | 16 hrs
Software/Hardware Requirements | 5 | 1 day | Wed 09-16-20 | Wed 09-16-20 | AK,H[1],S[1] | 8 hrs
Server Requirements | 6 | 1 day | Thu 09-17-20 | Thu 09-17-20 | AK,C[1],D[1] | 8 hrs
Enviroment Requirements | 7 | 1 day | Fri 09-18-20 | Fri 09-18-20 | AK,C[1],D[1],H[1],S[1],W[1] | 8 hrs
Usage/User Requirements | 8 | 1 day | Mon 09-21-20 | Mon 09-21-20 | AK,AL,CM,HS,MR | 40 hrs
Design Specifications |  | 9 days | Tue 09-22-20 | Fri 10-02-20 |  | 328 hrs
Basic context diagram of all modules | 9 | 2 days | Tue 09-22-20 | Wed 09-23-20 | AL,HS,CM | 48 hrs
Design Workflow | 11 | 2 days | Thu 09-24-20 | Fri 09-25-20 | CM,HS,MR,TS | 64 hrs
Front-end design of webpages | 12 | 3 days | Mon 09-28-20 | Wed 09-30-20 | AL,HS,MR,CM,TS | 120 hrs
Final High-Level Block diagram | 13 | 2 days | Thu 10-01-20 | Fri 10-02-20 | AK,AL,CM,HS,MR,TS | 96 hrs
Coding/Development |  | 30 days | Mon 10-05-20 | Fri 11-13-20 |  | 1,048 hrs
Create new front-end webpages using WordPress CMS | 14 | 4 days | Mon 10-05-20 | Thu 10-08-20 | AK,AL,CM,HS | 128 hrs
Edit the front-end pages to match the design workflow | 16 | 8 days | Fri 10-09-20 | Tue 10-20-20 | AK,AL,CM,HS,MR,TS | 384 hrs
Link to the back-end database server | 17 | 7 days | Wed 10-21-20 | Thu 10-29-20 | AL,MR,TS,HS | 224 hrs
Custom codes to meet the front-end requirements | 18 | 6 days | Fri 10-30-20 | Fri 11-06-20 | CM,HS,AL | 144 hrs
Site Optimization | 19 | 3 days | Mon 11-09-20 | Wed 11-11-20 | AK,MR,TS | 72 hrs
Code cleanup | 20 | 2 days | Thu 11-12-20 | Fri 11-13-20 | AK,AL,CM,HS,MR,TS | 96 hrs
Testing |  | 7 days | Mon 11-16-20 | Tue 11-24-20 |  | 224 hrs
Front-end testing of the webpages | 21 | 2 days | Mon 11-16-20 | Tue 11-17-20 | MR,TS | 32 hrs
Back-end testing | 23 | 2 days | Wed 11-18-20 | Thu 11-19-20 | CM,HS,MR,TS | 64 hrs
Database connectivity test | 24 | 2 days | Fri 11-20-20 | Mon 11-23-20 | AK,AL,CM,MR,TS | 80 hrs
Use-case/Integration testing | 25 | 1 day | Tue 11-24-20 | Tue 11-24-20 | AK,AL,CM,HS,MR,TS | 48 hrs
Training |  | 6 days | Wed 11-25-20 | Wed 12-02-20 |  | 160 hrs
Training plan | 26 | 2 days | Wed 11-25-20 | Thu 11-26-20 | CM,MR,TS | 48 hrs
Training materials | 28 | 1 day | Fri 11-27-20 | Fri 11-27-20 | MR,TS | 16 hrs
Training environment | 29 | 1 day | Mon 11-30-20 | Mon 11-30-20 | AK,CM,AL,HS,MR,TS | 48 hrs
Training test database | 30 | 2 days | Tue 12-01-20 | Wed 12-02-20 | MR,TS,CM | 48 hrs
Deployment |  | 3 days | Thu 12-03-20 | Mon 12-07-20 |  | 80 hrs
Deply site in real time | 31 | 2 days | Thu 12-03-20 | Fri 12-04-20 | AK,AL,CM,HS | 64 hrs
Customer review of live website | 33 | 1 day | Mon 12-07-20 | Mon 12-07-20 | AK,CM | 16 hrs
Documentation |  | 3 days | Tue 12-08-20 | Thu 12-10-20 |  | 136 hrs
Customer Feedback logs | 34 | 1 day | Mon 12-07-20 | Mon 12-07-20 | AL,CM | 16 hrs
Additional features | 36 | 1 day | Tue 12-08-20 | Tue 12-08-20 | AL,CM,HS | 24 hrs
Overall summary document | 37 | 2 days | Wed 12-09-20 | Thu 12-10-20 | AK,AL,CM,HS,MR,TS | 96 hrs